## Sheet1
Phase | Task Name | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Planning Phase | Topic Selection | bar: 10 to 17
Planning Phase | Background Research | bar: 13 to 24
Planning Phase | Project Proposal | bar: 18 to 2
Planning Phase | Requirement Gathering | bar: 25 to 7
Analysis Phase | Analyze Requirements | bar: 8 to 16
Analysis Phase | Define System Requirements | bar: 8 to 23
Analysis Phase | Feasibility Study (optional) | bar: 17 to 23
Design Phase | System Design (DFD, UI) | bar: 24 to 6
Design Phase | Database Design | bar: 1 to 6
Design Phase | System Architecture Design | bar: 7 to 11
Development Phase | Frontend Development | bar: 7 to 18
Development Phase | Backend Development | bar: 7 to 18
Development Phase | Database Setup | bar: 12 to 14
Development Phase | System Integration | bar: 15 to 18
Testing Phase | Unit Testing | bar: 19 to 25
Testing Phase | System Testing | bar: 26 to 2
Testing Phase | User Acceptance Testing | bar: 26 to 2
Testing Phase | Bug Fixing | bar: 26 to 10
Implementation Phase | Deployment | bar: 26 to 2
Implementation Phase | User Training (if needed) | bar: 26 to 10
Maintenance Phase | Monitoring & Bug Fixes | bar: 26 to 10
Documentation & Finalization | User Manual / Guide | bar: 26 to 10
Documentation & Finalization | Final Documentation | bar: 26 to 10
Documentation & Finalization | Project Defense Preparation | bar: 26 to 10
Documentation & Finalization | Final Submission | bar: 26 to 10
|  | February | [18 empty] | March | [30 empty] | April | [29 empty] | May